## Sprint i
Names and Contribution Percentage
ID | User Story | Task ID | Tasks | Sprint Number | Sprint Goal | Story Points | Story Points Completed | Zo | Kursten | Siaka | Liv | Meghann
| Establishing User Stories | 1 | Document User Stories | 0 | Establish the project foundation | 1 | 1 | 20 | 20 | 20 | 20 | 20
|  | 1.1 | Defined a style guide |  |  | 2 | 1 | 50 | 50
|  | 1.2 | Established ReadMe file |  |  | 1 | 1 |  | 100
|  | 1.3 | Established GitHub repo |  |  | 1 | 1 | 100
|  | 1.4 | Updated ReadMe and User Stories document | 1 | Enhance docs and UI | 1 | 1 |  | 50 |  | 50
|  | 1.5 | reviewed Style Guide file |  |  | 1 | 1 | 20 | 20 | 20 | 20 | 20
[6 empty] | 1 | 1
|  | 1.6 | Establish Backlog file |  |  | 2 | 2 | 30 |  | 70
|  | 1.6 | Started home page for the project front for the project |  |  | 2 | 2 |  |  |  |  | 100
1 | As a student, I want to track my assignment due dates in an easy-to-access central location. | 1.3.0 | Draft front end design | 2 | Begin Development in earnest | 1 | 1
|  | 1.3.1 | Develop based on design |  |  | 2 | 2
2 | As a student, my professors frequently update and change the syllabi for my classes and I want to get notifications of any changes so that I don’t miss any updates.
3 | As a student, I struggle with forgetting assignments are due until the due date is nearly here and I want a way to help not rush my assignments. I want to get automatic reminders about my upcoming deadlines.
4 | As a student, I want a planner that is easily shareable with my classmates and friends so that it’s easier for me to plan meetings, hangouts, and more.
5 | As a student worker, I want to be able to see my full schedule for the semester including classes, work, meetings, and other important events all in one place.
6 | As a student, often my professors adjust their due dates. When that happens, I want to be able to easily and quickly update my planner to reflect that.
7 | As a student, sometimes classes are cancelled due to snow. I want to be able to track any class schedule changes when this happens.
8 | As a user, I want to be able to use a planner for more than just school. I want to be able to use it for work, personal, family, or other events that are important to me.
9 | As a professional, I need quick and easy access to an accurate and dynamic academic calendar in order to schedule multiple appointments not related to university.
10 | As a user, I want an app to help me keep an accurate calendar reflecting my academic priorities for improved time management.
11 | As a student, I want control over my calendar so I can approve/reject automatically added events to my calendar, picking and choosing what is important to me.
12 | As a student, I want to easily add new assignments or deadlines to my planner without manually typing everything in.
13 | As a student, I want to be able to mark assignments as “in progress” or “completed” so I can track what I have already done better.
14 | As a student, I often overlook dates of assignments sandwiched between more important events. I want reminders of those “in-between” due dates before it's too late.
15 | As a tutor, I want to be able to add labels to due dates/ homework assignments so I am able to distinguish between my own school work and that of my mentees.
16 | As a non traditional student, I want to be able to quickly create a schedule that helps me work around my obligations outside of school.
| Miscellaneous | 1.0.0 | Update product backlog | 2 | Begin Development in earnest | 1 | 1
|  | 1.0.1 | update sprint backlog |  |  | 1 | 1
|  | 1.1.0 | Revise SRS |  |  | 1 | 1
|  | 1.1.1 | Fix backlogs |  |  | 1 | 1
|  | 1.1.2 | Retroactive github documentation |  |  | 1 | 1
|  | 1.2.0 | Create document |  |  | 1 | 1
|  | 1.2.1 | Explain Components and Their Relationships |  |  | 2 | 2
|  | 1.2.2 | Justify the Selection of the Architectural Pattern |  |  | 1 | 1
|  | 1.5.0 | Create use case descriptions |  |  | 2 | 2
|  | 1.5.1 | Create use case diagrams |  |  | 2 | 2
|  | 1.6.0 | Accurate issue tracking via github |  |  | 1 | 1
|  | 1.6.1 | Create SRS 2 |  |  | 1 | 1
|  | 1.4.0 | Create basic functionality |  |  | 6 | 5
|  | 1.4.1 | Create automated test command |  |  | 2 | 2

## Project Backlog (user stories)
Item description | Story ID | User story | points | Priority | Recommended subtasks
Project initiation (Deliverable 0 and 1) | 0 | Establishing User Stories | 1 | High | Document User Stories
|  |  | 1 | Medium | Defined a style guide
|  |  | 1 | Medium | Established ReadMe file
|  |  | 1 | High | Established GitHub repo
|  |  | 1 | High | Updated ReadMe and User Stories document
|  |  | 1 | High | Established and reviewed Style Guide file
|  |  | 1 | High | Started home page for the project front for the project
Update quickly and easily | 6 | As a student, often my professors adjust their due dates. When that happens, I want to be able to easily and quickly update my planner to reflect that.
| 7 | As a student, sometimes classes are cancelled due to snow. I want to be able to track any class schedule changes when this happens.
| 12 | As a student, I want to easily add new assignments or deadlines to my planner without manually typing everything in.
| 11 | As a student, I want control over my calendar so I can approve/reject automatically added events to my calendar, picking and choosing what is important to me.
Add clearly distinguishable labels at users discretion | 15 | As a tutor, I want to be able to add labels to due dates/ homework assignments so I am able to distinguish between my own school work and that of my mentees.
| 13 | As a student, I want to be able to mark assignments as “in progress” or “completed” so I can track what I have already done better.
Use for non-academic events | 9 | As a professional, I need quick and easy access to an accurate and dynamic academic calendar in order to schedule multiple appointments not related to university.
| 8 | As a user, I want to be able to use a planner for more than just school. I want to be able to use it for work, personal, family, or other events that are important to me.
| 16 | As a non traditional student, I want to be able to quickly create a schedule that helps me work around my obligations outside of school.
Notifications | 2 | As a student, my professors frequently update and change the syllabi for my classes and I want to get notifications of any changes so that I don’t miss any updates.
| 3 | As a student, I struggle with forgetting assignments are due until the due date is nearly here and I want a way to help not rush my assignments. I want to get automatic reminders about my upcoming deadlines.
| 14 | As a student, I often overlook dates of assignments sandwiched between more important events. I want reminders of those “in-between” due dates before it's too late.
See full callendar in one location | 1 | As a student, I want to track my assignment due dates in an easy-to-access central location.
| 5 | As a student worker, I want to be able to see my full schedule for the semester including classes, work, meetings, and other important events all in one place.
| 10 | As a user, I want an app to help me keep an accurate calendar reflecting my academic priorities for improved time management.
Shareable | 4 | As a student, I want a planner that is easily shareable with my classmates and friends so that it’s easier for me to plan meetings, hangouts, and more.

## Project
Story ID | Task description | # | Subtask description | Story points | Might not be possible currently | Already done
0 | Create starter documents | 0.0.0 | Document User Stories | 1
|  | 0.0.1 | Updated ReadMe and User Stories document | 1
|  | 0.0.2 | Established ReadMe file | 1
| Create github repo | 0.1.0 | Established github repo | 1
| Create Style guide | 0.2.0 | Defined a style guide | 2
|  | 0.2.1 | Established and reviewed Style Guide file | 1
| Begin building program | 0.3.0 | Started home page for the project front for the project | 2
1 | Update Backlogs | 1.0.0 | Update product backlog | 1
|  | 1.0.1 | update sprint backlog | 1
| Revise Sprint 1 Items | 1.1.0 | Revise SRS | 1
|  | 1.1.1 | Fix backlogs | 1
|  | 1.1.2 | Retroactive github documentation | 1
| Create the Architecture Design document | 1.2.0 | Create document | 1
|  | 1.2.1 | Explain Components and Their Relationships | 2
|  | 1.2.2 | Justify the Selection of the Architectural Pattern | 1
| Front End UI Creation | 1.3.0 | Draft front end design | 1
|  | 1.3.1 | Develop based on design | 2
| Early Development | 1.4.0 | Create basic functionality | 6
|  | 1.4.1 | Create automated test command | 2
| Use Cases | 1.5.0 | Create use case descriptions | 2
|  | 1.5.1 | Create use case diagrams | 2
| Proper Documentation | 1.6.0 | Accurate issue tracking via github | 1
|  | 1.6.1 | Create SRS 2 | 1